## ProjWBS
Project WBS Report
Time: 22:02:56
Date: 2022/12/13
From Period: 12/2009 Thru Period: 06/2023
Summary Selection: | Project Code
Level: | Project | Resp Type: |  | Co Code: |  | Use Maps: | N
Map Code: |  | Map Level: |  | A/S Values: | S
Multi Level Selection: | None
Restrict By Ind: | None | Budget: | Current | Status: | All
Min Value: |  | Currency: | Project | Chargeable: | Both Chargeable and Non Chargeable
Max Value: |  | Display Null Rows: | N
Project: | 1002268-FNB Branch Roll out 38
Phase | Task | Co | Org | RT | Project Currency | Cost | Effort | Revenue | Tot Bdgt Eff | Variance | Tot Backlog | Cost Variance | A/R (PTD) | Net Billing ex Tax | Unbilled (PTD) | Rev Adj | LMult
**** |  |  |  |  | ZAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMALIN |  |  |  |  | ZAR | 18813.19 | 37824.02 | 0 | 0 | -37824.02 | 0 | -18813.19 | 0 | 0 | 0 | 0 | 0
BOKSBU |  |  |  |  | ZAR | 24118.11 | 54246.06 | 0 | 0 | -54246.06 | 0 | -24118.11 | 0 | 0 | 0 | 0 | 0
BRIDGE |  |  |  |  | ZAR | 8612.26 | 19808.2 | 0 | 0 | -19808.2 | 0 | -8612.26 | 0 | 0 | 0 | 0 | 0
BRYANS |  |  |  |  | ZAR | 43282.25 | 96981.37 | 77915 | 77915 | -19066.37 | 0 | 423597.82 | 0 | 0 | 0 | 0 | 1.89
CHRIST |  |  |  |  | ZAR | 15774.64 | 34812.86 | 34812.86 | 80679.11 | 0 | 45866.25 | -15774.64 | 0 | 0 | 0 | 0 | 2.3
CIRCUS |  |  |  |  | ZAR | 41233.05 | 91501.88 | 91498.75 | 123586.29 | -3.13 | 32087.54 | -41233.05 | 0 | 0 | 0 | 0 | 2.3
DUBE |  |  |  |  | ZAR | 18529.05 | 42616.84 | 42618.39 | 70215 | 1.55 | 27596.61 | -18529.05 | 0 | 0 | 0 | 0 | 2.3
FNEWS |  |  |  |  | ZAR | 37543.72 | 86350.61 | 53121 | 53121 | -33229.61 | 0 | -14562.65 | 0 | 0 | 0 | 0 | 1.41
FOREST |  |  |  |  | ZAR | 50833.08 | 114826.77 | 79147 | 79147 | -35679.77 | 0 | -50833.08 | 0 | 0 | 0 | 0 | 1.59
GARDEN |  |  |  |  | ZAR | 24642.88 | 55907.52 | 55907.66 | 80380 | 0.14 | 24472.34 | 72652.24 | 0 | 0 | 0 | 0 | 2.3
GEZINA |  |  |  |  | ZAR | 31268.69 | 57491.61 | 57074.53 | 107779 | -417.08 | 50704.47 | -23454.35 | 0 | 0 | 0 | 0 | 2.28
LAGUNA |  |  |  |  | ZAR | 33130.72 | 72920.37 | 72920.4 | 84373.16 | 0.03 | 11452.76 | -33130.72 | 0 | 0 | 0 | 0 | 2.3
LANGEB |  |  |  |  | ZAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LETLHA |  |  |  |  | ZAR | 61629.02 | 118209.89 | 94681.7 | 99557.94 | -23528.19 | 4876.24 | -61629.02 | 0 | 0 | 0 | 0 | 1.74
MALL55 |  |  |  |  | ZAR | 18283.4 | 41465.53 | 24099.15 | 104557 | -17366.38 | 80457.85 | 26822.2 | 0 | 0 | 0 | 0 | 1.35
MAPONY |  |  |  |  | ZAR | 47419.19 | 107953.14 | 107948.65 | 115265 | -4.49 | 7316.35 | -47419.19 | 0 | 0 | 0 | 0 | 2.3
MATSAP |  |  |  |  | ZAR | 19832.5 | 45341.8 | 0 | 0 | -45341.8 | 0 | -19832.5 | 0 | 0 | 0 | 0 | 0
MIDDEL |  |  |  |  | ZAR | 20997.17 | 43332.08 | 36757.03 | 126000 | -6575.05 | 89242.97 | -20997.17 | 0 | 0 | 0 | 0 | 1.91
MOLOPO |  |  |  |  | ZAR | 43324.28 | 94933.57 | 94932.1 | 107319.62 | -1.47 | 12387.52 | -43324.28 | 0 | 0 | 0 | 0 | 2.3
NABOFI |  |  |  |  | ZAR | 12000 | 13200 | 13200.12 | 22200 | 0.12 | 8999.88 | -12000 | 0 | 0 | 0 | 0 | 0
NONQUE |  |  |  |  | ZAR | 1039.76 | 2391.46 | 0 | 0 | -2391.46 | 0 | -1039.76 | 0 | 0 | 0 | 0 | 0
NORTHR |  |  |  |  | ZAR | 12085.49 | 27062.22 | 0 | 0 | -27062.22 | 0 | -12085.49 | 0 | 0 | 0 | 0 | 0
PALMS |  |  |  |  | ZAR | 31821.74 | 72210.81 | 71313.29 | 76926.6 | -897.52 | 5613.31 | -31821.74 | 0 | 0 | 0 | 0 | 2.3
PORTSI |  |  |  |  | ZAR | 42120.19 | 93889.93 | 93087.8 | 135918.8 | -802.13 | 42831 | -42120.19 | 0 | 0 | 0 | 0 | 2.28
RANDPA |  |  |  |  | ZAR | 19344.3 | 44242.18 | 40350.5 | 71580.2 | -3891.68 | 31229.7 | 15887.52 | 0 | 0 | 0 | 0 | 2.1
Project WBS Report
Time: 22:02:56
Date: 2022/12/13
Phase | Task | Co | Org | RT | Project Currency | Cost | Effort | Revenue | Tot Bdgt Eff | Variance | Tot Backlog | Cost Variance | A/R (PTD) | Net Billing ex Tax | Unbilled (PTD) | Rev Adj | LMult
RWILSO |  |  |  |  | ZAR | 91019.45 | 209344.65 | 198198.03 | 198198.03 | -11146.62 | 0 | -91019.45 | 0 | 0 | 0 | 0 | 2.18
SEAPOI |  |  |  |  | ZAR | 34234.3 | 75598.94 | 75600.71 | 79044.66 | 1.77 | 3443.95 | -34234.3 | 0 | 0 | 0 | 0 | 2.3
SUMCRO |  |  |  |  | ZAR | 22503.44 | 51757.93 | 51758.08 | 64059 | 0.15 | 12300.92 | -22503.44 | 0 | 0 | 0 | 0 | 2.3
SWARTR |  |  |  |  | ZAR | 23577.26 | 46976.18 | 46978.32 | 75770.79 | 2.14 | 28792.47 | 14486.1 | 0 | 0 | 0 | 0 | 2.3
TABLEB |  |  |  |  | ZAR | 2252.79 | 5181.45 | 0 | 0 | -5181.45 | 0 | -2252.79 | 0 | 0 | 0 | 0 | 0
THULAM |  |  |  |  | ZAR | 25518.66 | 55173.95 | 44254.34 | 107242.68 | -10919.61 | 62988.34 | 29793.99 | 0 | 0 | 0 | 0 | 1.96
VIRGIN |  |  |  |  | ZAR | 37848.21 | 76850.91 | 55473.46 | 116236.92 | -21377.45 | 60763.46 | 5342.91 | 0 | 0 | 0 | 0 | 1.57
WESTON |  |  |  |  | ZAR | 49962.7 | 86644.18 | 69971.82 | 85723 | -16672.36 | 15751.18 | -47943.88 | 0 | 0 | 0 | 0 | 1.67
WILLOV |  |  |  |  | ZAR | 50033.36 | 93908.53 | 83420.46 | 86650.1 | -10488.07 | 3229.64 | -10044.86 | 0 | 0 | 0 | 0 | 1.98
WOODST |  |  |  |  | ZAR | 26827.28 | 60778.65 | 57194.76 | 88000 | -3583.89 | 30805.24 | -26827.28 | 0 | 0 | 0 | 0 | 2.16
XP |  |  |  |  | ZAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals |  |  |  |  | 0 | 1041456.13 | 2231736.09 | 1824235.91 | 2517445.9 | -407500.18 | 693209.99 | -187573.66 | 0 | 0 | 0 | 0 | 1.87
END OF REPORT

## ProjAnal
Project Analysis Report
Time: 08:17:03
Date: 2022/12/14
From Period: 12/2009 Thru Period: 06/2023
Summary Selection: | Project Code
Level: | Project | Resp Type: |  | Co Code: |  | Use Maps: | N
Map Code: |  | Map Level: |  | A/S Values: | S
Multi Level Selection: | None
Restrict By Ind: | None | Budget: | Current | Status: | All
Min Value: |  | Currency: | Project | Chargeable: | Both Chargeable and Non Chargeable
Max Value: |  | Display Null Rows: | N
Project | Name | Project Currency | Cost | Effort | Revenue | Tot Bdgt Eff | Variance | Tot Backlog | Cost Variance | A/R (PTD) | Net Billing ex Tax | Unbilled (PTD) | Rev Adj | LMult
1002443 | FNB - Campus Project | ZAR | 34959.85 | 73893.64 | 1245.66 | 97266 | -72647.98 | 96020.34 | 7197.13 | 0 | 82986 | -81740.34 | 0 | 0.04
112037 | FNB 2015 | NAD | 2044994.77 | 3565540.12 | 3587210 | 3587210 | 21669.88 | 0 | 571943.67 | 0 | 3587210 | 0 | 0 | 2.12
507120 | FNB Bank City - Leve | ZAR | 1681309.71 | 3592243.58 | 3600736.64 | 3887118.62 | 8493.06 | 286381.98 | -1810.28 | 0 | 3599607.63 | 1129.01 | 0 | 2.45
112798 | FNB Branch Roll out | ZAR | 1268253.98 | 2503354.56 | 2626091.63 | 2626091.63 | 122737.07 | 0 | 63241.1 | 0 | 2626091.63 | 0 | 0 | 2.43
113092 | FNB Branch Roll out | ZAR | 1195823.15 | 2264089.63 | 2334831.64 | 2334831.64 | 70742.01 | 0 | 41058.43 | 0 | 2334831.64 | 0 | 0 | 2.39
113332 | FNB Branch Roll Out | ZAR | 1113414.89 | 2318621.48 | 2334102.05 | 2334102.05 | 15480.57 | 0 | 26264.85 | 0 | 2334102.05 | 0 | 0 | 2.32
113749 | FNB Branch Roll out | ZAR | 1122761.19 | 2325573.53 | 2330871.57 | 2330871.57 | 5298.04 | 0 | 13092.41 | 0 | 2330871.57 | 0 | 0 | 2.31
500523 | FNB Branch Roll Out | ZAR | 1265361.77 | 2706068.73 | 2451281.64 | 2451281.64 | -254787.09 | 0 | -146558.35 | 0 | 2451281.64 | 0 | 0 | 2.08
1001495 | FNB Branch Roll Out | ZAR | 2273263.29 | 4676522.91 | 4270722.82 | 4307768.42 | -405800.09 | 37045.6 | -1189343.18 | 48909.5 | 4290145.52 | -19422.7 | 0 | 2.13
1001659 | FNB Branch Roll out | ZAR | 2060794.24 | 4411200.19 | 4088043.56 | 5724313.2 | -323156.63 | 1636269.64 | 492157.56 | 2030705.57 | 4795792.64 | -707749.08 | 0 | 2.12
1002037 | FNB Branch Roll Out | ZAR | 986244.2 | 2102647.04 | 1923698.93 | 2126403.56 | -178948.11 | 202704.63 | 659558.21 | 48613.95 | 1763489.32 | 160209.61 | 0 | 2.13
1002142 | FNB Branch Roll Out | ZAR | 1113818.55 | 2359344.05 | 2047717.46 | 3316361.16 | -311626.59 | 1268643.7 | 319525.96 | 670056.33 | 2221622.58 | -173905.12 | 0 | 2
1002268 | FNB Branch Roll out | ZAR | 1041456.13 | 2231736.09 | 1824235.91 | 2517445.9 | -407500.18 | 693209.99 | -187573.66 | 827568.74 | 1065440.12 | 758795.79 | 0 | 1.87
502533 | FNB Branch Rollout 2 | ZAR | 4120118.4 | 8131234.83 | 8498129.71 | 8498129.71 | 366894.88 | 0 | -785054.4 | 0 | 8498129.71 | 0 | 0 | 2.31
505206 | FNB Branch Rollout 2 | ZAR | 1814738.45 | 3797353.83 | 3908766.84 | 3908766.84 | 111413.01 | 0 | -1631614.45 | 0 | 3908766.84 | 0 | 0 | 2.37
507088 | FNB Branch Rollout 2 | ZAR | 3230538.48 | 6284501.49 | 6644437.04 | 6644437.04 | 359935.55 | 0 | -299369.18 | 0 | 6644437.04 | 0 | 0 | 2.34
508606 | FNB Branch Rollout 3 | ZAR | 2417014.58 | 4941425.55 | 5236516.16 | 5236516.16 | 295090.61 | 0 | -75333.58 | 0 | 5236516.16 | 0 | 0 | 2.45
1000743 | FNB Branch Rollout 3 | ZAR | 2725501.98 | 5775141.29 | 5776105.44 | 5776105.44 | 964.15 | 0 | 2241328.02 | 0 | 5776105.44 | 0 | 0 | 2.3
1001629 | FNB Branches Roll ou | ZAR | 237025.05 | 537867.25 | 1579218 | 1579218 | 1041350.75 | 0 | 610087.22 | 0 | 1579218 | 0 | 0 | 6.81
1001794 | FNB Branches Roll ou | ZAR | 1335904.61 | 2771573.54 | 1616338.26 | 2553290.98 | -1155235.28 | 936952.72 | 122654.2 | 223091.95 | 1354140.38 | 262197.88 | 0 | 1.29
1002113 | FNB Engineering Proj | ZAR | 135296.63 | 262199.71 | 236543.51 | 256065 | -25656.2 | 19521.49 | 65813.3 | 195040 | 256065 | -19521.49 | 0 | 2.07
1001488 | FNB Eswatini | SZL | 2218276.84 | 5450045.56 | 2770016.34 | 2828673 | -2680029.22 | 58656.66 | -1111551.84 | 645572.75 | 3031281.54 | -261265.2 | 0 | 1.37
110496 | FNB Tanzania Expansi | USD | 50542.14 | 103768.61 | 108493.5 | 108493.5 | 4724.89 | 0 | 3674.47 | 0 | 108493.5 | 0 | 0 | 2.42
503812 | Sekhametsi FNB Offic | LSL | 2473643.05 | 3627136.32 | 3768509.66 | 3768509.66 | 141373.34 | 0 | -30030.26 | 0 | 3768509.66 | 0 | 0 | 2.33
507991 | Trump Street FNB | ZAR | 57801.31 | 126183.05 | 121260.55 | 121260.55 | -4922.5 | 0 | -4356.31 | 0 | 121260.55 | 0 | 0 | 2.19
Totals |  | 0 | 38018857.24 | 76939266.58 | 73685124.52 | 78920531.27 | -3254142.06 | 5235406.75 | -224998.95 | 4689558.79 | 73766396.16 | -81271.64 | 0 | 2.2
END OF REPORT

## ARStatus
A/R Status Report
Time: 08:18:04
Date: 2022/12/14
From Period: 12/2009 Thru Period: 06/2023
Summary Selection: | Project Code
Level: | Project | Resp Type: |  | Co Code: |  | Use Maps: | N
Map Code: |  | Map Level: |  | A/S Values: | S
Multi Level Selection: | None
Companies: | None
Organizations: | None
Accounts: | None
Aging1: | 30 |  | Restrictions: | None
Aging2: | 60 |  | Min Value:
Aging3: | 90 |  | Max Value:
Aging Date: | 2022-12-14
Inquiry Type: | History
Display Currency: | Company
Project Name: | FNB Branch Roll Out 37
Project Code | Doc Nbr | IG | Doc Date | Per Billings | Per Collect | A/R | 2022-01-30 | 31 - 60 | 61 - 90 | Over 90 | Unallocated | Days Old | Nbr Of Docs | Money Days | Total Aged | Avr Days
1002142 | 185947 | ** | 2022-06-14 | 92524.4 | 92524.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 185979 | ** | 2022-06-20 | 123612.4 | 123612.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 185981 | ** | 2022-07-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 185988 | ** | 2022-06-20 | 23115 | 23115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 186189 | ** | 2022-06-27 | 108278.66 | 108278.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 186283 | ** | 2022-06-28 | 97046.87 | 97046.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 186664 | ** | 2022-07-25 | 100139.7 | 100139.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 186666 | ** | 2022-07-25 | 69577.3 | 69577.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 186693 | ** | 2022-07-25 | 10752.5 | 10752.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 186699 | ** | 2022-07-25 | 83500.21 | 83500.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 186732 | ** | 2022-07-29 | 119443.6 | 119443.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 186823 | ** | 2022-07-29 | 96775.95 | 96775.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 186987 | ** | 2022-08-19 | 130502.64 | 130502.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 187100 | ** | 2022-08-24 | 75842.5 | 75842.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 187101 | ** | 2022-08-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 187102 | ** | 2022-08-24 | 53649.8 | 53649.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 187117 | ** | 2022-08-25 | 90387.88 | 90387.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 187209 | ** | 2022-08-30 | 92323.98 | 92323.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 187305 | ** | 2022-08-31 | 138570.4 | 138570.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A/R Status Report
Time: 08:18:04
Date: 2022/12/14
Project Code | Doc Nbr | IG | Doc Date | Per Billings | Per Collect | A/R | 2022-01-30 | 31 - 60 | 61 - 90 | Over 90 | Unallocated | Days Old | Nbr Of Docs | Money Days | Total Aged | Avr Days
1002142 | 187307 | ** | 2022-08-31 | 10120 | 10120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 187612 | ** | 2022-09-21 | 81012.9 | 81012.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 187613 | ** | 2022-09-21 | 95478.06 | 95478.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 187614 | ** | 2022-09-21 | 98014.5 | 98014.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 187615 | ** | 2022-09-21 | 79592.88 | 79592.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 188390 | ** | 2022-10-31 | 14547.5 | 14547.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 188574 | ** | 2022-11-08 | 15674.5 | 0 | 15674.5 | 0 | 15674.5 | 0 | 0 | 0 | 36 | 1 | 564282 | 15674.5 | 36
1002142 | 188909 | ** | 2022-11-28 | 10803.1 | 0 | 10803.1 | 10803.1 | 0 | 0 | 0 | 0 | 16 | 1 | 172849.6 | 10803.1 | 16
1002142 | 188910 | ** | 2022-11-28 | 10803.1 | 0 | 10803.1 | 10803.1 | 0 | 0 | 0 | 0 | 16 | 1 | 172849.6 | 10803.1 | 16
1002142 | 189006 | ** | 2022-11-30 | 10752.5 | 0 | 10752.5 | 10752.5 | 0 | 0 | 0 | 0 | 14 | 1 | 150535 | 10752.5 | 14
1002142 | 189009 | ** | 2022-11-30 | 100847.41 | 0 | 100847.41 | 100847.41 | 0 | 0 | 0 | 0 | 14 | 1 | 1411863.74 | 100847.41 | 14
1002142 | 189072 | ** | 2022-11-30 | 16204.65 | 0 | 16204.65 | 16204.65 | 0 | 0 | 0 | 0 | 14 | 1 | 226865.1 | 16204.65 | 14
1002142 | 189094 | ** | 2022-11-30 | 107796.68 | 0 | 107796.68 | 107796.68 | 0 | 0 | 0 | 0 | 14 | 1 | 1509153.52 | 107796.68 | 14
1002142 | 189116 | ** | 2022-11-30 | 113762.23 | 0 | 113762.23 | 113762.23 | 0 | 0 | 0 | 0 | 14 | 1 | 1592671.22 | 113762.23 | 14
1002142 | 189117 | ** | 2022-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002142 | 189118 | ** | 2022-11-30 | 122271.86 | 0 | 122271.86 | 122271.86 | 0 | 0 | 0 | 0 | 14 | 1 | 1711806.04 | 122271.86 | 14
1002142 | 189119 | ** | 2022-11-30 | 62240.3 | 0 | 62240.3 | 62240.3 | 0 | 0 | 0 | 0 | 14 | 1 | 871364.2 | 62240.3 | 14
1002142 | 189120 | ** | 2022-11-30 | 98900 | 0 | 98900 | 98900 | 0 | 0 | 0 | 0 | 14 | 1 | 1384600 | 98900 | 14
Totals |  |  |  | 2554865.96 | 1884809.63 | 670056.33 | 654381.83 | 15674.5 | 0 | 0 | 0 | 180 | 11 | 9768840.02 | 670056.33 | 14.58
END OF REPORT

## ARAnal
A/R Analysis Report
Time: 08:17:45
Date: 2022/12/14
From Period: 12/2009 Thru Period: 06/2023
Summary Selection: | Project Code
Level: | Project | Resp Type: |  | Co Code: |  | Use Maps: | N
Map Code: |  | Map Level: |  | A/S Values: | S
Multi Level Selection: | None
Companies: | None
Organizations: | None
Accounts: | None
Aging1: | 30 |  | Restrictions: | None
Aging2: | 60 |  | Min Value:
Aging3: | 90 |  | Max Value:
Aging Date: | 2022-12-14
Inquiry Type: | History
Display Currency: | Company
Project Code | Project Name | Per Billings | Per Collect | A/R | 2022-01-30 | 31 - 60 | 61 - 90 | Over 90 | Unallocated | Days Old | Nbr Of Docs | Money Days | Total Aged | Avr Days
1002443 | FNB - Campus Project | 95433.9 | 95433.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
507120 | FNB Bank City - Leve | 4139548.77 | 4139548.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112798 | FNB Branch Roll out | 2969434.17 | 2969434.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113092 | FNB Branch Roll out | 2606776.02 | 2606776.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113332 | FNB Branch Roll Out | 2660876.32 | 2660876.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113749 | FNB Branch Roll out | 2657193.54 | 2657193.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500523 | FNB Branch Roll Out | 2799994.35 | 2799994.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1001495 | FNB Branch Roll Out | 4933667.38 | 4884757.88 | 48909.5 | 48909.5 | 0 | 0 | 0 | 0 | 27 | 1 | 1320556.5 | 48909.5 | 27
1001659 | FNB Branch Roll out | 5515161.54 | 3484455.97 | 2030705.57 | 500040.95 | 1530664.62 | 0 | 0 | 0 | 159 | 4 | 82591461.78 | 2030705.57 | 40.67
1002037 | FNB Branch Roll Out | 2028012.72 | 1979398.77 | 48613.95 | 37810.85 | 10803.1 | 0 | 0 | 0 | 127 | 5 | 1215348.75 | 48613.95 | 25
1002142 | FNB Branch Roll Out | 2554865.96 | 1884809.63 | 670056.33 | 654381.83 | 15674.5 | 0 | 0 | 0 | 180 | 11 | 9768840.02 | 670056.33 | 14.58
1002268 | FNB Branch Roll out | 1225256.13 | 397687.39 | 827568.74 | 745142.08 | 82426.66 | 0 | 0 | 0 | 210 | 12 | 13316922.22 | 827568.74 | 16.09
502533 | FNB Branch Rollout 2 | 9722582.63 | 9722582.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
505206 | FNB Branch Rollout 2 | 4506165.03 | 4506165.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
507088 | FNB Branch Rollout 2 | 7641102.83 | 7641102.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
508606 | FNB Branch Rollout 3 | 5978714.7 | 5978714.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000743 | FNB Branch Rollout 3 | 6587068.03 | 6587068.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1001629 | FNB Branches Roll ou | 1816100.71 | 1816100.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1001794 | FNB Branches Roll ou | 1557261.45 | 1334169.5 | 223091.95 | 10512.15 | 212579.8 | 0 | 0 | 0 | 126 | 4 | 7532565.55 | 223091.95 | 33.76
1002113 | FNB Engineering Proj | 294474.75 | 99434.75 | 195040 | 195040 | 0 | 0 | 0 | 0 | 42 | 3 | 2730560 | 195040 | 14
1001488 | FNB Eswatini | 6431189.77 | 5785617.02 | 645572.75 | 507665.2 | 138061.65 | 0 | -154.1 | 0 | 192 | 12 | 8016210.6 | 645572.75 | 12.42
A/R Analysis Report
Time: 08:17:45
Date: 2022/12/14
Project Code | Project Name | Per Billings | Per Collect | A/R | 2022-01-30 | 31 - 60 | 61 - 90 | Over 90 | Unallocated | Days Old | Nbr Of Docs | Money Days | Total Aged | Avr Days
503812 | Sekhametsi FNB Offic | 6896455.75 | 6896455.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
507991 | Trump Street FNB | 139449.63 | 139449.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals |  | 85756786.08 | 81067227.29 | 4689558.79 | 2699502.56 | 1990210.33 | 0 | -154.1 | 0 | 1063 | 52 | 126492465.42 | 4689558.79 | 26.97
END OF REPORT